## Slide 1: Getting through accreditation
Experiences from an Austrian university

## Slide 2
Roland HUMER
Magister in International Business Administration from WU
M.A. in Balkan Studies from the University of Vienna
3 yr work experience at WU
3+ yr work experience as consultant for universities
IUQB: Irish Universities Quality Board: member of the IRIU Register of Reviewers
Republic of Bulgaria Council of Ministers / National Evaluation and Accreditation Agency: member of expert pool for accreditations

## Slide 3: Results produced
200 pp self-evaluation report
  Including graphs, tables, pictures
70 pp appendix
  Lists, figures
Peer review visit
  4 peers meet approx. 100 internal and external stakeholders

## Slide 4: Project organisation
Dean:
Chapter Strategy
Final decisions
Vice-Dean 1:
Project owner
Other Vice-Deans
Professors:
Information held
locally
Feedback
Project manager
+ assistant:
Coordination,
realisation
Middle managers
/ experts:
Write chapters,
prepare data
Middle managers
/ experts:
Write chapters,
prepare data

## Slide 5: Project staff
1 project manager: 1 yr part-time, 1 yr full-time
1 project assistant: 1 yr part-time
Sub-contractors: senior consulting, proof-reading, layout, catering
+ considerable time of Dean, Vice-Dean and many employees

## Slide 6: Embedding at the institution
Sub-groups and management boards
  Accreditation board with approx. 20 representatives, approx. 8 meetings
Management boards
  Regular oral reports
Employees
  Articles in university newspaper
  2 internal info sessions
  Intranet website

## Slide 7: Process 1: preparation
Study accreditation scheme
  Detect projects, data and documents needed
  Create and agree on an index for the self-evaluation report
Learn from others’ experience
  Read self-evaluation reports
  Exchange with comparable institutions
Team building
  Define tasks
  Define responsibilities

## Slide 8: Process 1: preparation
Cooperation with accreditation agency
  Visit to clarify expected results / problem areas
  Constant exchange, questions
Internal communication
  Explains aims and processes
  Get employees involved, get support of all decision-makers
Duration: 1 year

## Slide 9: Process 2: self-evaluation report
Duration: 9 months
Dean and vice-deans write chapter on strategy
  Broad internal discussion
  Senior consultancy – feedback
  Guideline / example for other chapters

## Slide 10: Process 2: self-evaluation report
Production of chapters
  Production by middle-managers, OK by vice-dean
  Revision and OK by project team
  Discussion with accreditation board
Making one report out of 10 chapters
  Editing, discussion etc.
Senior consultancy – feedback
Finalisation
  Proof-reading, layout, printing, etc.

## Slide 11: Process 3: peer review visit
Duration: 3 months
Creation of schedule, selection of representatives
Briefing of representatives
  Process, expectations, tasks,…
  Senior consultancy – briefings
  Briefings by dean and vice-dean
Other: hotel, catering, establishment of a room for peer reviewers, etc.

## Slide 12: Language
Self-analysis vs. marketing
  Set a positive tone
  Use buzzwords like “world class”, “state of the art”, … only when can be proved
  Admit major problem areas and give explanations and solutions
  Precise descriptions for external readers
English vs. local

## Slide 13: Re-Accreditation
Re-use / update texts of earlier accreditation
Make reference to major changes and recommendation
Keep up the momentum among team members and employees