## Slide 1: IMPLEMENTATION OF PROJECT ACTIVITIES OCTOBER 2011 – JUNE 2012 -Strategic Support for the Development of Sustainable QA Structures at the Newly Public University in Kosova no. 517482-
Mjellma Carabregu, WUS Kosova

## Slide 2: Activities of QA@UPPz implemented until June 2012
Establishment of 'Experts Team' for QA Strategy (1.1) – May 2012
Drafting the status quo report (1.2) (on QA) – January 2012
Kick off meeting (1.3) & training workshop: December 7-8, 2011
Study visit & Development of QA methodology (1.4) in Osnabrueck: March 27 – 31, 2012

## Slide 3
Establishment of QA structures (2.1): March 2012 – (QA Officer appointed – Jasmin Jusufi, QA Office established, QA model ToR sent by EU partner institutions, QA officer participated in the study visit in HSO)
Establishment of International Relation Office (2.2): January 2012 – ongoing (International Relations Coordinator appointed – Mrs. Nuran Mallta – Muhaxheri, IRO model ToRs sent by the EU partners, IR Coordinator participated in the study visit @HSO)

## Slide 4
Finalization of budget & contracting (MNGT); project website & logo (DISS).
QA Strategy Development – 2nd workshop (1.5) and a project meeting: June 26-27 in Prizren.